## Schedule
| Pete Bajo Mine Project | Effort Estimate in days | Planned Start Date | Planned End Date
1 | Phase One 5205 Airdoors Install | 24 days | Mon 10/29/18 | Thu 11/29/18
1.1 | Order Materials | 25 days | Mon 10/1/18 | Fri 11/2/18
1.1.1 | Delivery of Materials | 1 day | Mon 10/22/18 | Mon 10/22/18
1.1.2 | Remove Top Doors | 6 days | Mon 10/22/18 | Mon 10/29/18
1.1.3 | Install Top doors | 6 days | Tue 10/30/18 | Tue 11/6/18
1.1.4 | Remove Lower Doors | 6 days | Wed 11/7/18 | Wed 11/14/18
1.1.5 | Install Lower Doors | 6 days | Thu 11/15/18 | Thu 11/22/18
1.2.1 | Phase One Ops Drift Development for Fans | 24 days | Mon 11/5/18 | Thu 12/6/18
1.2.2 | Order Materials | 6 days | Mon 10/1/18 | Mon 10/8/18
1.2.3 | Delivery of Materials | 1 day | Mon 11/5/18 | Mon 11/5/18
1.2.4 | Shoot Left Rib (Newmont) | 6 days | Mon 11/4/19 | Mon 11/11/19
1.2.5 | Cable Bolts Left Rib (SMD) | 6 days | Tue 11/12/19 | Tue 11/19/19
1.2.6 | Shoot Right Rib (Newmont) | 6 days | Wed 11/20/19 | Wed 11/27/19
1.2.7 | Cable Bolts Left Rib (SMD) | 6 days | Thu 11/28/19 | Thu 12/5/19
2.1.1 | Phase Two Cross Cut Airdoors Install | 25 days | Thu 12/6/18 | Wed 1/9/19
2.1.2 | Order Materials | 49 days | Mon 10/1/18 | Thu 12/6/18
2.1.3 | Delivery of Materials | 1 day | Wed 12/5/18 | Wed 12/5/18
2.1.4 | Remove Top Doors | 6 days | Thu 12/6/18 | Thu 12/13/18
2.1.5 | Install Top doors | 6 days | Fri 12/14/18 | Fri 12/21/18
2.1.6 | Install Top doors | 6 days | Fri 12/14/18 | Fri 12/21/18
2.1.7 | Remove Lower Doors | 6 days | Mon 12/24/18 | Mon 12/31/18
2.1.8 | Install Lower Doors | 7 days | Tue 1/1/19 | Wed 1/9/19
3.1.1 | Phase Three Leeville Airdoors | 13 days | Wed 1/9/19 | Fri 1/25/19
3.1.2 | Order Materials | 73 days | Mon 10/1/18 | Wed 1/9/19
3.1.3 | Delivery of Materials | 1 day | Wed 1/9/19 | Wed 1/9/19
3.1.4 | Remove Doors | 7 days | Thu 1/10/19 | Fri 1/18/19
3.1.5 | Install Doors | 6 days | Mon 1/21/19 | Mon 1/28/19
4.1.1 | Phase Four Civil and Fan Install | 20 days | Wed 1/9/19 | Tue 2/5/19
4.1.2 | Delivery of Fan and Evase | 0 days | Mon 1/7/19 | Mon 1/7/19
4.1.3 | Form and Pour Pedestals | 6 days | Wed 1/9/19 | Wed 1/16/19
4.1.4 | Form and pour Pad | 7 days | Thu 1/17/19 | Fri 1/25/19
4.1.5 | Fan and Bulkhead Installation | 7 days | Mon 1/28/19 | Tue 2/5/19
4.2.1 | Phase Four Fan Removal | 6 days | Wed 2/6/19 | Wed 2/13/19
4.2.2 | Remove old Fan | 6 days | Wed 2/6/19 | Wed 2/13/19
4.2.3 | Remove Bulkhead | 6 days | Thu 2/14/19 | Thu 2/21/19

## Network Diagram
Pete Bajo Mine Project
Phase 1 | Phase 2 | Phase3 | Phase 4
The network diagram is a precendence diagramming method that identifies:
-the tasks that must be completed before other tasks can begin
-the tasks that can be done while other tasks are being performed
1.1
5205 Airdoors Install
2.1
Two Cross Cut Airdoors Install
3.1
Three Leeville Airdoors Install
4.1.1
Civil and Fan Install
1.2
Ops Drift Development for Fans
4.2.1
Old Fan Removal